## Gantt Chart Template
| PROJECT TITLE | Catan Game |  |  |  |  | COMPANY NAME | [8 empty] | Team 15
| PROJECT MANAGER | Yash and Nelson |  |  |  |  | DATE | [8 empty] | 23/01/2023
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation / Planning
1.2 | Project Scope | Yash | 24/01/23 | 27/01/23 | 3 | 100% | bar: WEEK 1 T to WEEK 1 R; WEEK 2 W to WEEK 2 F
1.3 | Project Planning Document | Nelson | 24/01/23 | 31/01/23 | 7 | 100% | bar: WEEK 1 T to WEEK 2 F
2 | Agile Sprint Cycles 1
2.1 | Scope and Task Cards | Yash | 2023-02-02 | 2023-04-02 | 2 | 22% | bar: WEEK 2 M to WEEK 3 M
2.2 | Requirement and risk analysis | Nelson | 2023-03-02 | 2023-05-02 | 2 | 16% | bar: WEEK 2 M to WEEK 3 T
2.3 | Design | Eddie | 2023-05-02 | 2023-07-02 | 2 | 0% | bar: WEEK 3 T to WEEK 3 W
2.4 | Code Generation | Morgan/ Ryan | 2023-07-02 | 17/2/23 | 10 | 0% | bar: WEEK 3 W to WEEK 5 F
2.5 | Testing | Noah | 17/2/23 | 19/2/23 | 2 | o% | bar: WEEK 5 T to WEEK 5 W
2.6 | Review | Yash/ Nelson | 19/2/23 | 21/2/23 | 2 | 0%
3 | Agile Sprint Cycles 2
3.1 | Scope and Task Cards | Nelson | 21/2/23 | 23/2/23 | 2 | 0%
3.2 | Requirement and risk analysis | Yash | 23/2/23 | 26/2/23 | 3 | 0% | bar: WEEK 5 M to WEEK 6 T
3.3 | Design | Noah | 26/2/23 | 28/2/23 | 2 | 0% | bar: WEEK 6 T to WEEK 6 W
3.4 | Code Generation | Morgan/Ryan | 2023-01-03 | 13/3/23 | 13 | 0% | bar: WEEK 6 W to WEEK 8 F
3.5 | Testing | Eddie | 13/3/23 | 16/3/23 | 3 | 0% | bar: WEEK 8 F to WEEK 9 T
3.6 | Review | Nelson/Yash | 16/3/23 | 18/3/23 | 2 | 0% | bar: WEEK 9 T to WEEK 9 W
4 | Agile Sprint Cycles 3
4.1 | Scope and Task Cards | Nelson | 18/3/23 | 21/3/23 | 3 | 0% | bar: WEEK 9 W to WEEK 9 F
4.2 | Requirement and risk analysis | Yash | 21/3/23 | 23/3/23 | 2 | 0% | bar: WEEK 9 F to WEEK 10 M
4.3 | Design | Noah | 23/3/23 | 24/3/23 | 1 | 0% | bar: WEEK 10 M
4.4 | Code Generation | Morgan/Ryan | 24/3/23 | 2023-02-04 | 9 | 0% | bar: WEEK 10 T to WEEK 11 F
4.5 | Testing | Eddie | 2023-02-04 | 2023-04-04 | 2 | bar: WEEK 11 F to WEEK 12 M
4.6 | Review | Nelson/Yash | 2023-04-04 | 2023-06-04 | 2 | 0% | bar: WEEK 11 M to WEEK 12 T
5 | Group Report
5.1 | Report on WWW and EBI | Everyone | 13/3/23 | 21/4/23 | 1 | 0% | bar: WEEK 12 W to WEEK 12 R
6 | Peer Assessment Report
6.1 | Give Out Points | Everyone | 25/4/23 | 27/4/23 | 2 | 0% | bar: WEEK 12 R
7 | Video
7.1 | Record a Walkthrough of the Prototype | Ryan/Morgan | 27/4/23 | 28/423 | 1 | 0% | bar: WEEK 12 R to WEEK 12 F

## Try Smartsheet
Try Smartsheet for Free